## Sheet1
user stories | Issue key | Status
Create UX & UI screen for group calling | SIM-14 | Done
Test the maximum users that can be connected to one group call using peer to peer architecture | SIM-15 | Done
Create Face recognition model using tensor flow | SIM-16 | Done
Analysis and implementation of facial recognition model using tensor flow | SIM-18 | Done
Connect to Agora RTC Server to enable group video calling | SIM-25 | Done
create tables and stored procedures to save and retrieve data | SIM-27 | In Progress
ux changes for better interactivity | SIM-31 | Done
Implement video conference ui using agora react component library | SIM-32 | Done
Face recognition implementation using deepface | SIM-33 | Done
Research on deepface | SIM-34 | Done
Create a web api using flask to connect to face recognition code | SIM-35 | Done
Implement face recognition in ui | SIM-36 | Done
Implement UI to mark attendance | SIM-17 | To Do
Test facial recognition model | SIM-19 | In Progress
Enable attendance marking feature to room owners | SIM-20 | To Do
Enable screen sharing feature | SIM-21 | To Do
Test whole application and implementation of auto attendance system | SIM-22 | To Do
create tables and stored procedures to save and retrieve data | SIM-27 | In Progress
Technical paper and documentation | SIM-28 | To Do
Deployment Procedure | SIM-29 | To Do
Test of whole application functionality | SIM-30 | To Do